## Wasaga Distribution
Schedule for Wasaga Distribution Inc. - 2024 Cost of Service
OEB File Number: EB-2023-0055
Updated: December 15, 2023
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [5 empty] | 2023-10-20 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2023-10-20 | 100%
| 3 | OEB Issues Completeness Letter |  | 2023-11-03 | 0 |  | 2023-11-03 | 2023-11-03 | 100%
Notice & Procedural Order No. 1 | 4 | OEB Issues Notice of Hearing | 10 | 2023-11-13 | 7 |  | 2023-11-10 | 2023-11-10 | 100%
| 5 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2023-11-18 | 12 |  | 2023-11-15 | 2023-11-17 | 100%
| 6 | Notice of Hearing Publication Date |  |  | 17 |  | 2023-11-20 | 2023-11-10 | 100%
| 7 | Intervention Request Close | 25 | 2023-11-28 | 24 |  | 2023-11-27 | 2023-11-27 | 100%
| 8 | OEB Issues Procedural Order No. 1 | 35 | 2023-12-08 | 27 |  | 2023-11-30 | 2023-11-30 | 100%
Discovery Process | 9 | OEB staff Files Draft Issues List | 45 | 2023-12-18 | 35 |  | 2023-12-08 | 2023-12-06 | 100%
| 10 | Decision on Issues List |  | 2023-11-03 | 41 |  | 2023-12-14 | 2023-12-13 | 100%
| 11 | OEB staff Files Interrogatories |  |  | 42 |  | 2023-12-15 | 2023-12-15 | 100%
HOLIDAY BREAK (December 16, 2023, TO January 7, 2024, INCLUSIVE – 23 DAYS)
| 12 | Intervenors File Interrogatories | 60 | 2024-01-25 | 44 |  | 2024-01-09 | 2024-01-09 | 100%
| 13 | Applicant Files Responses to Interrogatories | 80 | 2024-02-14 | 68 |  | 2024-02-02
Settlement Process | 14 | Settlement Conference Held | 90 | 2024-02-24 | 87 |  | 2024-02-21
| 15 | Settlement Progress Letter Filed |  |  | 90 |  | 2024-02-24
| 16 | Settlement Proposal Filed | 115 | 2024-03-20 | 108 |  | 2024-03-13
| 17 | OEB staff Submission on Settlement Proposal Filed | 122 | 2024-03-27 | 115 |  | 2024-03-20
Hearing | 18 | Presentation of Settlement/Oral Hearing | 130 | 2024-04-04 | 123 |  | 2024-03-28
Argument Process | 19 | Applicant's Argument-in-chief Filed | 140 | 2024-04-14 | 134 |  | 2024-04-08
| 20 | OEB staff and Intervenor Argument Filed | 150 | 2024-04-24 | 144 |  | 2024-04-18
| 21 | Applicant's Reply Argument Filed | 170 | 2024-05-14 | 165 |  | 2024-05-09
Decision | 22 | Decision Issued | 230 | 2024-07-13 | 221 |  | 2024-07-04
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I7
Performance Standard Date = [Performance Standard Days Elapsed]+I7+23
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7+23
Actual Date = Table1[[#This Row],[Case Schedule Date Approved]]