## GDAR GI List
GI# | WorkFlow | Status | Issue Description | Suggested Resolution | Final Resolution | Schema Affected | Schema Changes Required | Issue Submit Date | Date of Last Status Change | Requestor | Company
001 | VS | O | Can Consumers notify RTS (Return to System) via phone? There were concerns raised that it should be done in writing. | GDAR does not specifically require that the RTS be submitted in writing other than the rescind of the STR. Union plans to accept RTS requests by phone. Union notes: * all requests are documented by CRRs into our source system * as with other consumer requests, due diligence will be done to ensure the identity of the requester (e.g. validation terms) * scripting for RTS will include ensuring consumer acknowledges potential impacts and encourage them to contact their vendor first There is an exemption request from EGD on the need for the rescind to be in writing is currently being evaluated by OEB. The outcome of this request may dictate the approach |  |  |  | 2003-12-07 |  | BC-1 | Union/Enbridge Business Checkpoint Oct 8-
002 | ALL | O | How to change effective date for a processed STR | "Update" action is only available for STRs with a state = "Suspended-AI", per GDAR. To change the effective date of a processed STR, vendor must submit one or more other STRs. Example: Add Consumer Nov 1 is processed. To change effective date to Dec 1, submit a delete consumer request followed by another add consumer request for Dec 1. To change effective date to Oct 1, submit another Add Consumer transaction effective Oct 1- the first STR will be marked "Overwritten". Notifications are triggered in all cases. |  |  |  | 2003-12-07 |  | BC-2 | Union/Enbridge BC Oct 8-
003 | SV- VV | O | Can UGL reject for things other than invalid account number | Distributors will only mark STRs as "Rejected" if the STR fails |  |  |  | 2003-12-07 |  | BC-3 | Union/Enbridge BC Oct 8-
004 | OTHER | O | Format of Message board notification | The format of CSV file that will be used for message notifications by Enbridge is attached. A separate CSV file will be provide for each combination of STR status (e.g. pending, rescinded, stopped, implemented, or overwritten) and consumer notification type (e.g. move to a different vendor or move to system gas). |  |  |  | 2003-12-07 |  | BC-4 | Union/Enbridge BC Oct 8-
005 | OTHER | O | When will Enbridge and UGL align on format of the message board notification? | Enbridge will look align the format of its message board notification with Union following the implementation of EnTRAC Phase 1. Given existing testing timelines, it is not feasible to change the existing design prior to implementation. This may be delivered within the scope of Phase 2 (Sept 2003) |  |  |  | 2003-12-07 |  | BC-5 | Union/Enbridge BC Oct 8-
006 | SV VV VS | O | Consider renaming update action. | "UpdateConsumer" request will be renamed to "TransferConsumer". |  |  |  | 2003-12-07 |  | BC-6 | Union/Enbridge BC Oct 8-
007 | TECH | O | Why full response files rather than partial? |  |  |  |  | 2003-12-07 |  | BC-7 | Union/Enbridge BC Oct 8-
008 | TECH | O | Trans -ID at document level vs. STR ID # |  |  |  |  | 2003-12-07 |  | BC-8 | Union/Enbridge BC Oct 8-
009 | CCL | O | Will EGD customers who move out of the franchise area…..be retained on the existing supply arrangement on the inactive account? | Enbridge does not have the capability to maintain an inactive account on an existing supply arrangement. Once the account is finalized it is removed from the supply arrangement |  |  |  | 2003-12-07 |  | BC-9 | Union/Enbridge BC Oct 8-
010 | CCL | O | Do we supply effective date for customers moving to new delivery area? Mark to confirman earlier "yes" response to this question | The earliest effective date will be included. The effective date will be calculated as the next 1st of the month that is at least 12 days from notification (not requested move date). Vendors have the ability to update this date. If the update is not timely, the STR could remain Suspended-AI requesting a new effective date. |  |  |  | 2003-12-07 |  | BC-10 | Union/Enbridge BC Oct 8-
011 | CCL | O | Enbridge to confirm service address change in comparison to Union | The Enbridge Service Address Change process will not be identical to that presented by Union. Enbridge will make best efforts to determine the new account for a customer that moves within the Enbridge franchise area (the best manner for doing this is still being determined). This account will be attached to the agreement under the terms the old account had. If there is a significant time lag in identifying the new account number, Enbridge will look to the vendor for confirmation of the contract parameters (pool and price point). Old accounts will not be retained on the existing supply arrangement as an inactive account |  |  |  | 2003-12-07 |  | BC-11 | Union/Enbridge BC Oct 8-
012 | SV VV VS | O | Distribute collision matrix Enbridge and Union have worked to prepare a revised collision matrix that is consistent between the two organizations | Enbridge is currently preparing this for distribution, with descriptions to assist in interpreting the matrix. This is expected to be ready for distribution by December 5 / 03. |  |  |  | 2003-12-07 |  | BC-12 | Union/Enbridge BC Oct 8-
013 | OTHER | O | Enbridge to follow up with format for consumption data report | A copy of the Pool Consumption Report specifications for EnTRAC are attached |  |  |  | 2003-12-07 |  | BC-13 | Union/Enbridge BC Oct 8-
014 | OTHER | O | Distribute documentation and schemas for non-GDAR Unionline enhancements | Non-GDAR Union Gas schemas will be posted on Union's website at www.uniongas.com during the week of Dec 1. |  |  |  | 2003-12-07 |  | BC-14 | Union/Enbridge BC Oct 8-
015 | OTHER | O | Ability to designate charge to contract ID for consumption look up | Union will continue to ask vendors to designate a charge-to contract up front. Given the proposed design change to waive charge for the first 5,000 account each month, this should eliminate charges for ad-hoc users and therefore eliminate the need for a per-request bill-to contract id |  |  |  | 2003-12-07 |  | BC-15 | Union/Enbridge BC Oct 8-
016 | OTHER | O | Ability to include consumption with "ADD" response | Gas Supply STR is meant to facilitate only a change in gas supply. Addition of this data would be inconsistent that principle and would not be consistent with EGD. Union recognizes the discomfort with respect to fee for use and will make the following adjustment to it's design: In any month, the first 5,000 consumption requests will not attract a charge. Requests over and above that limit, will attract a charge of $1.00 per successful history retrieval. |  |  |  | 2003-12-07 |  | BC-16 | Union/Enbridge BC Oct 8-
017 | OTHER | O | Consider keeping the contract id and price point id in the Monthly Account Activity file | Union will continue to include the contract id and price point id in the MAA file |  |  |  | 2003-12-07 |  | BC-17 | Union/Enbridge BC Oct 8-
018 | DELETE | O | Distribute Soft copy of presentation | As per D. Charleson email sent 13-Oct |  |  |  | 2003-12-07 |  | TS-1 | Union/Enbridge Technical Checkpoint Oct 9-
019 | TRANS | O | Availability and timing of unattended file transfer for EGD | EGD does not have an unattended file transfer within the current scope of EnTRAC. This decision was based on the fact that no vendors are currently using the Unionline functionality. EGD will consider providing this functionality as an enhancement following the implementation of Phase 2 (Sept / 04), if there is demand from the marketplace. |  |  |  | 2003-12-07 |  | TS-2 | Union/Enbridge TC Oct 9-
020 | TECH | O | Is the Tag name required when there will not be any value/data to send with a particular field | Tag names are not required for optional fields. Some field are nullable. Instance representation eliminates need to provide empty tag field for non-applicable STR types |  |  |  | 2003-12-07 |  | TS-3 | Union/Enbridge TC Oct 9-
021 | TECH | O | What are the batch/document size limitations (i.e. Max. # of STRs per batch) (UGL/EGD) | Union will increase its transaction count size limitation to 9,000 with the desired effect to find the optimum balance between the resulting advantages from few batch submissions and ensuring available processing time is shared equally between the entire vendor community (as a benchmark reference please note a batch of 3000 records requires approximately 30 minutes of internal processing time). |  |  |  | 2003-12-07 |  | TS-4 | Union/Enbridge TC Oct 9-
022 | TECH | O | How do you tie request and response documents together (audit/tracking) AND each subsequent submission of each record | Each subsequent submission of each record comes from a new request document and therefore will be tracked separately in terms of request/response pairings but the STR tracking itself is maintained. The vendors will be able to track their documents by the VendorReferenceNumber that they can specify in their request documents, and is repeated over the multiple response documents that relate to the original request. In addition, document creation date is being expanded to include a timestamp to ensure uniqueness of response documents. |  |  |  | 2003-12-07 |  | TS-5 | Union/Enbridge TC Oct 9-
023 | ?? | O | Can the Notification be split per STR type | For the non-requestor there is only one STR type (i.e. Delete). |  |  |  | 2003-12-07 |  | TS-6 | Union/Enbridge TC Oct 9-
024 | TECH | O | Response strategy – Option 1 – return only STRs that have changed (many responses) vs return whole batch in response flagging items that change | The current Request and Response strategy (i.e. full Response regardless of change) will be maintained. Drivers that could trigger a change to an incremental include adoption of Business to Business (B2B) technology |  |  |  | 2003-12-07 |  | TS-7 | Union/Enbridge TC Oct 9-
025 | TECH | O | Add functional ability to allow operator to down load entire batch with latest states (assuming Option 1 – STR response) | See Response October 9th Technical Item #7. Distributors will not be changing its Response strategy at this time. |  |  |  | 2003-12-07 |  | TS-8 | Union/Enbridge TC Oct 9-
026 | TECH | O | Assign “sequence #” to response file names (potential solution requirement) | Duplicate item. See response for October 9 Technical Item 7. |  |  |  | 2003-12-07 |  | TS-9 | Union/Enbridge TC Oct 9-
027 | ALL | O | How many error codes do we expect to be common and how many unique (EGD/Union). Common + Utility+Specific Reason codes will be defined | The Utilities have yet to define these codes. They are not expected to be defined until end of November. |  |  |  | 2003-12-07 |  | TS-10 | Union/Enbridge TC Oct 9-
028 | OTHER | O | How to introduce/drop reason codes, post implementation | A protocol will be developed that is comparable to the protocol proposed for addressing changes to the common schemas. Protocol should be expanded to include all changes that impact stakeholders |  |  |  | 2003-12-07 |  | TS-11 | Union/Enbridge TC Oct 9-
029 | TECH | O | How does Vendor detect and notify Utility if Utility’s document is invalid - document & STR level? | The response documents and notifications should never be invalid at the document level as they will be built as to the published schemas. Any deviation from this would be considered an application error that should be reported to the utility. Questions about the validity of specific STR's should be directed to the business support contacts within the utility for the applications as the first point of contact |  |  |  | 2003-12-07 |  | TS-12 | Union/Enbridge TC Oct 9-
030 | DELETE | O | Vendor expressed some concern that current support model is inadequate | This was cleared up after a discussion at break. The comments were based on an early Unionline experience which has since been remedied. Union will continue to employ the same support model with GDAR implementation. |  |  |  | 2003-12-07 |  | TS-13 | Union/Enbridge TC Oct 9-
031 | TECH | O | Provide documentation on the security measures (Sapient) | Security considerations have been an important aspect from day one of the design and implementation of the GDAR solutions for both UG and EGD. The following are the common security mechanisms built into both solutions: Authentication: A user cannot access Unionline or EnTRAC unless they have a valid user id and a password Authorization: Every user with a unique user id has roles and priveleges assigned to them in both Unionline and EnTRAC. Based on these priveleges, one vendor cannot view or updat e the data that belows to another vendor. Encryption: Both Unionline and EnTRAC use the SSL-based secure http (https) protocol and employs 128-bit encryption. On the server side, both employ 1024-bit RSA encrypted certificates issued by a third party. The unattended file transfer capability in place for Unionline also employs digital certificates issued by a third party (VeriSign) |  |  |  | 2003-12-07 |  | TS-14 | Union/Enbridge TC Oct 9-
032 | TECH | O | Ability to send STRs with Vendor specific ID that would be included in all subsequentresponses (recognized nice to have) | A new tag is being added to the Gas Supply request/response document for vendor supplied STR ID. The value will be echoed back in the original first response only. The vendor would then be required to update their internal systems to record the utility-defined STR ID |  |  |  | 2003-12-07 |  | TS-15 | Union/Enbridge TC Oct 9-
033 | DELETE | O | Documenting Business Rules that cause change to states or collisions | This effort is now expected to be addressed within the GDAR Implementation Working Group facilitated by the OEB |  |  |  | 2003-12-07 |  | TS-16 | Union/Enbridge TC Oct 9-
034 | OTHER | O | Can there be a single date for a rollout of the UGL and EGD GDAR Implementations? | The Utility plans are not currently tied to a single date. Both are working towards supporting a March 1 GDAR implementation. Internal dependencies may not allow a common date. Further investigation to be done once implementation plans are more fully developed |  |  |  | 2003-12-07 |  | TS-17 | Union/Enbridge TC Oct 9-
035 | OTHER | O | Is there flexibility around the implementation date? | Both Union and Enbridge have limited flexibility given the March 1 GDAR implementation deadline. Significant changes in the implementation date would need to be acknowledged by the Ontario Energy Board |  |  |  | 2003-12-07 |  | TS-18 | Union/Enbridge TC Oct 9-
036 | DELETE | O | Vendors to communicate to UGL & Enbridge any dependencies or constraints that they have with respect to implementation dates for GDAR | Reminder included on 30-Oct communication for Vendors to submit responses |  |  |  | 2003-12-07 |  | TS-19 | Union/Enbridge TC Oct 9-
037 | OTHER | O | Direct requested a Pilot to assess the possibility of a Pilot Phase before rolling out theGDAR Solution. | Union has noted Direct's desire to participate in a pilot program |  |  |  | 2003-12-07 |  | TS-20 | Union/Enbridge TC Oct 9-
038 | DELETE | O | UGL and Enbridge to coordinate on the GDAR solution details communication/educational | Both Utilities are willing to work together on these sessions as they are needed. Vendors are to identify specific questions or areas requiring additional clarification to allow for planning of such sessions. |  |  |  | 2003-12-07 |  | TS-21 | Union/Enbridge TC Oct 9-
039 | DELETE | O | Vendors to complete their review of the schemas at an attribute level and provide comments back the Utilities | Reminder included on 30-Oct communication for Vendors to submit responses |  |  |  | 2003-12-07 |  | TS-22 | Union/Enbridge TC Oct 9-
040 | OTHER | O | Protocol for change management of common elements of GDAR solution post-implementation should be part of the SLA | This effort is now expected to be addressed within the GDAR Implementation Working Group facilitated by the OEB. |  |  |  | 2003-12-07 |  | TS-23 | Union/Enbridge TC Oct 9-
041 | SV |  | Will the Enbridge new home lookup (account number lookup) process work as per the Union Gas documentation? Union documentation demonstrates that if account number is found, customer is enrolled and account number is returned in response file. As per Phase 1A for EnTRAC, a two-step process is required to lookup the account number and then enroll |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
042 | CCL |  | How will customer moves work in each utility? How will we be notified? How do we provide notification? What are the rules at each utility for identifying seamless moves? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
043 | SV VV VS |  | In the workflow section of the documentation, it states that an STR can be moved to a rescind state by and Admin the ‘their’ behalf. On whose behalf? The customer? What are the rules surrounding this being done by EGD? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
044 | SV VV VS |  | Why would an STR move from a pending state to rejected? What scenarios would trigger this transition? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
045 | SV |  | How will the quasi add process work? The map is very limited and does not provide the required detail |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
046 | VV |  | Union documentation indicates that XML notification will be issued to the non-originator of an STR. What will the media for this be for Enbridge? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
047 | CCL |  | For customer moves, the documentation states that this information will be issued in XML format but not posted on the message board. How will the information be transferred to us? What are the schema details? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
048 | ALL |  | Is it possible to receive final transition states (other than rejected) for an STR when processing initial response? For example, can a new add request be responded to with ‘overwritten’ right away? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
049 | OTHER |  | Why will Union Gas not be performing the Security Deposit validation? Will this change and if so, when? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
050 | SV VV VS |  | When do the 14 and 30-day rescission windows start? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
051 | SV VV VS |  | How do STRs become overwritten? Can this occur based on STRs from other brokers? Contextual examples are required here |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
052 | SV |  | Are we notified of all state transitions or will we only receive the current state when the file is generated? For example, if a customer state is pending at 12:00 and the processed at 5:00, will we ever see the pending state? What is the trigger for the update? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
053 | SV VV VS |  | How are new account numbers provided in rejected responses? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
054 | VS |  | Inactive accounts were previously automatically removed from supply agreements upon anniversary maintenance. New documentation states that this will no longer happen. Either the customer? or us must remove the account. How is this to be done? Would the delete transaction be used? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
055 | SV |  | Will there be a unique identifier on accounts that are created as add requests by the utility? How will these accounts be distinguished from accounts that were sent incorrectly by us? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
056 | CCL |  | Documentation indicates that service address changes will ‘always be honoured’. What do this mean? Examples are required |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
057 | SV VV VS |  | If there are already 2 pending STRs, all other incoming STRs will be rejected. Can we attempt the STR again at a later date? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
058 | ALL |  | What are the scenarios that can cause an incoming STR to coexist with a processed STR? Only 1 example was provided |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
059 | OTHER |  | What values other than delivery area will be contained in the ‘additional info’ element? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
060 | OTHER |  | What is the transaction that will be used to request consumption? What are the details of the schema? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
061 | TECH |  | What are the schema details for the supply change notification? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
062 | VV |  | How do we determine the difference between a return to system and a switch to another broker? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
063 | TECH |  | The account number is listed as a required field. How can a required field be left blank? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
064 | SV VV VS |  | For account number lookups, the street number for the customer is required. What about rural addresses? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
065 | TECH |  | Tag is required for customer name when the value is blank. Why is this only required for name and not other values? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
066 | TECH |  | City value is limitted to 20 characters. Is this long enough? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
067 | TECH |  | Gas Vendor Account Number value is limitted to 25 characters. Can this be increased to 50? |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
068 | TECH |  | In the Gas Supply Change Response, the schema document indicates that the status value can be blank. Status must always be returned on a response. Also, reason and reason code should be populated with each response - confirm this for accepted responses |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
069 | TECH |  | Additional information value is required when when we submit to an invalid pool based on delivery area |  |  |  |  | 2003-12-07 |  | Beth Brooks | Direct Energy
070 | TECH |  | Confirm that address information is echoed and not supplimented with utility details in all response records
071 | SV | C | In a GasSupplyChange Response, the transitive state of "Pending" is not needed by the retailers-it provides no value- and is currently not defined as mandatory in the flow of response states ( ie it can be skipped if the state in the distributor's system changes to "processed" prior to the transmittal of the response). This also is cause for additional programming/logic that is unneeded. | Propose to remove the 'Pending' status. If it can not be removed from code/design, then distributors could suppress it from being transmitted. If state must be maintained then it should be a mandatory state with rules around it's use. Distributors to respond back with whether they can suppress it/remove it. Union/Enbridge will ensure it is a predicatble status. Kitchener can do it as well, but not as a first choice. | It was suggested that all parties will make "Pending" a mandatory state change in the processing flow. 'Pending' always comes back to the Retailer before receiving a transaction status of Processed, Suspended or Rejected states ('Need to Verify' flow is covered under a separate GI number). Union and Enbridge to check costs and respond back with agreement or dissent. Jan 08: It was noted that this state and the need for "Acknowledgement" of recieved data is tied to exchange of all transactions. A new GI is opened ( #082) to deal with the broader issue. This issue is closed and the issue captured under 82. | GasSupplyChangeResponse | No Change Required. | 2003-12-10 |  | GP | Work group
072 | SV TECH | O | The Initial Screening for a switch request calls for a 2 of 3 match on Account number (always) and one of either the postal code or the customer name. An exact match on customer name is impractical as it relies on too many variables. Suggested that a Name Validator similar to electricity be used. This would require the addition of a new field on the schema and documented business rules. | Need to add a "Name Validator" field to provide for the 2 of 3 acceptance validation. The Name vaildator would be defined as the first four characters of the billing name as it appears on the customer bill excluding any spaces or special characters. DEC 16-03: Name validator not accepted by all (Kitchener can not do validator - JAN14:Loraine stated Kitchener they can do this, Kingston can,Union can and Enbridge to come back with response). Must be exact full name match. Suggested should include special characters and spaces- and suffix Mr /Mrs. Etc- as it appears as the billing name. Postal code must be billing/mailing adress postal code- no space. Agreed?Account number stripped of special characters spaces etc (a space is considered a special character). For Account Number Lookup STRS: Account number lookup needs billing address/or service address? Need to confirm which way.Also, we must fill out service address info plus name fields in full(?). The only time 2/3 occurs is on the frst CGS TX - after that , the account number is the only data used for identifying the customer-Agreed by all.Company name is first 4 or if there is a last name and a company name.Need to come to agreement on validation requirements. JAN08: Kitchener has a separate Company Name field in their system and are willing to map to last name. Suggested- Postal Code validator= billing address postal code (no space), account number -no spaces special characters. name= under discussion. (On Union bill there is no name but there is a service address without a postal code. Kitchener's bill has the service address and the mailing address - only the billing addres has a postal code- the name captured is the billing address name. Kingston is flexible and will accomodate but can only put the billing address postal code. Enbridge to check. | Proposal: Account Number= no spaces/ no special characters. Postal code Validator= Billing Address Postal Code (no spaces) to be populated in he Billing Address Postal Code field (mailing and billing are synonymous). Name Validator - first four characters of the Last Name or Company Name as appropriate populated in the Las Name Field. Company Name( if applicable) will be populated in the Last Name field. Retailers must provide all 3 fields even though a 2/3 match is only required for validation criteria. | GasSupplyChangeRequest | Change Billing Postal code field and Last Name field to Mandatory - required to be populated. | 2003-12-10 |  | GP | Working group
073 | SV TECH | O | The GasSupplyChange Response Tx currently mirrors back the customer name and address info as was provided in the GSCRequest sent by the Vendor. The distributor has the dbase of record and therefore the distributor should be providing back the customer info as it is recorded in their system. This allows the vendor to have the most recent updated info for that customer. | Revise the technical requirements for the customer name and address fields to require that the fields on the Response transaction are populated by the distributor with the info as it resides in their system.Should the distributor respond with customer info from their system , the reatiler is required to use the info. Union notes that they offer monthly downloads that provides for customer info updates for all vendor customers and therefore mirrors our info. Kitchener and Kingston will provide back their system info - not mirror back retailers info. Enbridge only mirrors. |  | GasSupplyChangeResponse | The Account Information details should be populated by the distributor - not mirrored from the request Tx OR need to change schema definition to allow for mirrored and for updated info to be populated. | 2003-12-10 |  | GP | Working group
074 | SV TECH | C | The current GasSupplyChange request and response schema does not have a field for Company Name. This is required | Need to add a new field for "Company Name" | All Agreed to provide the Company Name in the Last Name field of the schema as a business rule to be followed by all. | GasSupplyChange Request and Response | no change | 2003-12-10 | 2003-12-16 | GP | Working group
075 | SV | C | Where an Account number is not provided by the Vendor on a GasSupplyChange Request, the Account Information details should be mandatory | Suggested that when the account number is not provided ( ie account number needs to be looked up)- the business rule should be stated that all the service address and name fields are actually required- as applicable (the schema is optional). Suggested that those field usage rules need to be revised in the description document and in the Business Process document | For Account Number Look-up Requests the following fields must be populated by the Retailer on the schema: The Primary service address fields- 'Street Number', 'Street Name', 'Unit #' if applicable, postal code. The customer Last Name field. All agreed to this business rule. | GasSupplyChange Request | No change needed | 2003-12-10 | 2004-01-08 | GP | Working group
076 | SV | C | In a GasSupplyChange Response, the transitive state of "Need to Verify" is not needed by the retailers-it provides no value- The response of "processed" will be returned with the correct account number assigned | Propose to remove the 'Need to Verify' status. If it can not be removed from code/design, then distributors could suppress it from being transmitted. Distributors to respond back with whether they can suppress it/remove it. | All agreed that the 'Need to Verify' state is a mandatory state sent back to the Retailer in the process flow. Always the first response sent back to the Retailer from the vendor for account numebr look-up request STRs. The "Processed" state will be returned to the Retailer within 14 days- the clock does not stop for Account Number look-up requests. Awaiting for response from Union that 1 day will remain (turnaround time)- clock on the 14 days will stop-all others agreed. Jan 08: need to discuss the need for this state in the process flow in relation to GI #082. revised previous statement re:clock will stop on the 14 days for acount number look-ups. This item is closed. | GasSupplyChange response | No Change | 2003-12-10 | 2004-01-08 | GP | Working group
077 | SV | REFERSC | Historical Consumption is required by all retailers for customer switches. Currently today consumption is provided back coincident with the reserve response. Although there is a set of consumption request schema, it is more effective to have the consumption data included in the GasSupplyChange Response | Ammend the GSC response to include the historical consumption fields- question 12 months or 24 as per GDAR? -If the complete separate fields can not be provided then suggested that the annual consumption be provided under additional info tag.Total should beprovided in m3.- read in m3.DEC 16-03: Kitchener can provide monthly detail HC for accepted GSC requests. Union and Enbridge said no- scope creep- big change. Kingston said can provide the annual consumption- aggregated. No resolution yet - pending scope issue referred to the Steering Committee. |  | GasSupplyChange Response | Add fields to capture the historical Consumption - 12 or 24 months? | 2003-12-10 | 2003-12-10 | GP | Working group
078 | SV | C | Verify that in the GSC Response transaction that if delivery area provided in the GSCRequest is in error, that the corrected DSA info will be provided in the response. | Suggested that it should be as is for Union | Union provides back a suspend response and notes under Additional Info fields, the correct DSA for the contract. Enbridge has only two so not an issue. Kithchner and Kingston don’t have DSAs' no issue. | GasSupplyChange Response | No change | 2003-12-10 | 2003-12-16 | GP | Working group
079 | SV | C | Consistenecy between the dates for supply to begin - for most distributors , flow is aligned to the 1st day of a given month- Kingston switches on a read date -Also, each distributor needs a different lead time prior to flow- Union 58 days, Enbridge 52 days, Kingston 20 days, Kitchener(90)- why are there max leadtime differences between the utilities? | Is there an opportunity to align the lead times? | Kitchener has noted that it will be 60 days from receipt of a complete and valid STR plus to the 1st of a month. Enbridge neeeds 33 days (revised) coincidsent with GDAR, Kingston will turn on the 1st of a month as well. No opportunity to align however, all agreed to provide for transfer at 1st of a month regardless of meter read date. |  |  | 2003-12-10 | 2003-12-16 | GP | Working group
080 | SV | O | GDAR calls for the implementation of a switch request to be completed within 60 days.It appears that in reality, based on lead times required by distributors, completion is more like 90 days. How /can we address this ? | LDC s will respond back as to why they require the lead times stipulated by them. It was noted by some that upstream supply arrangements take approx 35 days alone- Union offered to outline process timeframes at the next meeting. |  |  |  | 2003-12-10 |  | GP | Working group
081 | ALL | O | Kitchener has stated that if the STR comes with an account number and postal code only, that due to Privacy Act (and/or municipal by-laws) they can not provide back customer name and address information.Same issue with Customer moves, they cannot provide new address information, they can only tell us that the customer moved. Enbridge also noted that further investagtion internally was required wrt whether warranty of possesion of an LOA was sufficient for them. | Need to address this. |  |  |  | 2004-12-16 |  | GP | Working group
082 | ALL | O | There appears to be a difference of interpretation regarding the definition and application of "Pending" as captured in GDAR - this needs discussion. In association with this discussion , need to discuss the "states" proposed in the Union/Enbridge design. | Jan 14, 2004: Looking at the first occurance in GDAR of 4.3.3.4. CCK is saying they see only 2 states "Pending" (with a reason of Suspended AI, Verification completed) and "Implemented" (flowing or billing change). 2 issues that come to light are we need to define pending also go over what happens during that period. We agree that pending in GDAR is part of the happy path going from 1.3 to 1.4 to 1.6 (ie. processed to processed to implemented). This common understanding ties in with what Union presented on slide 18. ECG is to validate how their system handles this. Jan 15, 2004: Libby came back with how their system is designed to handle pending. Once they have "processed" and account number it is no longer pending and is thereby open to be taken by another vendor or go back to system. Discussion is still needed. |  |  |  | 2004-01-08 |  | GP | Working group
083 | ALL | O | Need to discuss the requirement of transactional ackowledgement (AA) in response to TX exchange and the model to be implemented for exchange (ie receiving all TXs repeatedly or response to each TX) Also related is the currentl process in which a whole file is rejected when only some transactions are bad.
084 | TECH | O | Need to discuss invalid reposnse file protocols/acknowledgement and the process to recover (reference to GI 29) |  |  |  |  | 2004-01-08 |  | GP | Working group
085 | OTHER | O | How are customer information changes communicated.
086 | TECH | O | Is there an opportunity to have a separate schema for Account Number Look-ups |  |  |  |  | 2004-01-08 |  | GP | Working group
087 | SV | O | We have an issue that for people in arrears (Suspended SD), Union puts them on a deal (unless inactive ie. not burning gas). EGD to check to see if they suspend based on arrears (if account locked/service cut off "Red Flagged"). Kingston doesn't endorse this rule 4.3.5.7. (about monitoring when the customr pays their bill) and this rule is not alligned to a 45 day default. Kingston would suspend (default). Kitchener doesn't know, but they have similar concerns as Kingston. If we there is an arrears suspend how long is it held? The STR is still pending so no other vendors can collide with this STR. Once issue resolved we should update EBT document by adding or removing examples. We need greater clarity around the GDAR definition of default. 4.3.3.6. suspending STR. | Jan 14, 2004:Gas distributor to review how 4.3.3.6 and 4.3.5.7. will be handled, check their logic. Jan 15, 2004: Union's take now is that the suspension just suspends the timeline then the clock continues where it left off. |  |  |  | 2004-01-14 |  | TW | Working Group
088 | ALL | O | Data consistency needs to be implemented. Examples of this are, Commodity Sales Service (CSS) should be System Gas. Enrol versus add? What is proper? | Ensuring all documents have consistent naming. Whenever and item is identified (ie. Commodity Sales Service vs System Gas) then at the point the person responsible for the appropriate reports should update. We should be monitoring this at each meeting and identifying when we need to change some wording. |  |  |  | 2004-01-14 |  | TW | Working Group
089 | All | R | 4.3.3.1.b does GDAR require account lookup? We need guidance from Steering Committee. If they say yes required, we need to update our flow for lookup. Is it part of the 14 days? Is it triggered by the orginal STR or is a second STR required? | Union design allows for the accounnumber and enrol in one flow. UK and KU are willing to do it but using a separate flow and schema. |  |  |  | 2004-01-14 |  | TW | Working Group
090 | ALL | O | Multiple reasons for Suspensions? 30 days for each occurence could delay an STR could make this take 1 year. Should all errors be identified. Change of Schema would be required if identifying all the errors.Also need to clarify the intent of the 30 day interval in GDAR 4.3.4.1 | Jan 14th, 2004: We would prefer to get all errors at the same time, if they are aware. Jan 15th, 2004: 4.3.4.1. means that clock stops but resumes where it stopped, based on what Libby brought to the table on Jan 15th. Libby confirmed the first error may create a subsequent error, so a single error message will be sent for the first piece of data. The maximum timing to clear up a suspension should be a 30 day block of time.This is not agreed. |  |  |  | 2004-01-14 |  | TW | Working Group
091 | ALL | O | Define text for Reasons for suspensions at a later date and then apply to schema. | Need to address this. |  |  |  | 2004-01-15 |  | TW | Working Group
092 | ALL | R | We need clarity on what a processed state is. Pending in GDAR means that its not implemented. Union/EGD says processed isn't pending so if another Vendor also signed this customer up then they can bump. Kitcehner, Direct, OESC feel that a customer is pending until flow. Kingston can go either way. Union stated for the record that if we do have pending until the implementation date, this would be a very easy scenario because it avoids collisions. Should pending be up to the point of flow or to the point of processed? GDAR is ambiguous but our interpretation is Pending until Implemented (which is flow)...At which point would a second Enrol STR be accepted? 30 days from receipt of STR, is this how long pending is? How long is pending? Screening of 14 days, 30 days, or 44 days. | If we answer, at which point would a second Enrol STR be accepted?. Then this will solve this. Direction needed by Steering Committee on interpretation of 4.3.3.4. Another way to look this is can an STR be overwritten on the effective date or when processed. Does 4.6.1. mean to get into a processed state or flow. ECG interprets it as processed. GDAR . We need to get direction from the board on their vision...ie. flow will happen in 60 days or just the effective date the vendor wants. |  |  |  | 2004-01-15 |  | TW | Working Group
093 | ALL | R | Steering committee issue, the LDC's ECG, Union can currenlty let a vendor hold a customer for up to 150 days. Reserve used to be 180 days, then at 90 days Union would ask what was being done with the customer. What will the timeline be and still be GDAR compliant? |  |  |  |  | 2004-01-15 |  | TW | Working Group
094 | ALL | O | Need to Verify. How do we know when the 14 days started in a 1 STR process? |  |  |  |  | 2004-01-15 |  | TW | Working Group
095 | TECH | O | Could schema (1.2.2.3.10 of Schema Design - Gas Supply Change <Page 68 of 96>) terminology be Accepted instead of Processed? In addition, does the existing schema have the right labels? Should overwritten be taken out? Vendor A submits and its accepted, say it gets processed, then Vendor A wants to change the Effective Date, this should be overwritten (pending resolution of Global Issue 082). |  |  |  |  | 2004-01-15 |  | TW | Working Group
096 | ALL | O | Vendor can rescind on EGD 30 days prior to flow (customer has 14 days). On Union this wouldn't be a rescind STR, but we have 40 days prior to flow we would have to submit a remove STR. When does rescind transaction get used? We should be able to rescind. We are unclear if it goes to the end of the 44 days or all the way to the implementation date. |  |  |  |  | 2004-01-15 |  | TW | Working Group
097 | TECH | O | Can we add a new action code, ie. "UPD TRANS". What limit do we have, what is being verified? What if we submit a new account number or name, that will be validated again. |  |  |  |  | 2004-01-15 |  | TW | Working Group
098 | ALL | O | Need to understand what an STR is or covers. Is an STR only an original transaction request to transfer a customer or does it include updates and changes/rescinds etc to a transfer request. Reference GDAR 4.3.3.5 |  |  |  |  | 2004-01-21 |  | GP | Working group
099 | ALl | C | In a Suspended scenario - why are there two transitive states needed ( SD and AI)- security should just be another reason code. Union does not use it but Enbridge does. | Clarified that in a Suspend for insufficent security, there is no requirement for the vendor to return an Update response. The vendor arranges for security and then the transfer process continues as normal. A susopend for AI ( additional information), the vendor must return revisions to the distributor with an update transction in order for processing to continue. | All agreed that separate status' are required - one for securiy and onr for additional information needed. | N/A |  |  | Jan 21-04 | GP | Working group
100 | ALL | O | Need to define all the reject or suspend reasons and what they mean.
101 | ALL | O | WRT customer default, Enbridge and Union state that they will not Suspend processing of a transfer request, they will simply proces it regardless. Kitchener will also process it through and Kingston will suspend.Issue arose as to how long they have to hold the suspended state- retailer suggest that they must hold the suspend until default is cleared - no agreement to the interpretation of GDAR 4.3.5.5. | Suggest Kingston review their position regarding suspending a transfer for customer default or implement functionality to suspend the transfer request indefintiely until custoemr arrears is cleared. |  |  |  |  | Jan 21-04 | GP | Working group
102 | SV | O | Union/Enbridge design for changing info to a "Processed" but not "Implemented" STR does not appear to allow for info changes - Union suggests that vendor would have to rescind or delete the STR and resend a new one again. Enbridge suggests possibly a Delete STR should be sent and a new STR again. Vendors and KU and UK disagree- the Vendor should be able to simply send an update to the existing accepted STR. | [5 empty] | Jan 21-05 | GP | Working group
103 | SV | O | When an Add /Update is sent, how does the distributor know what piece of information is to be changed ? Is the vendor to populate all fields or only the field(s) where changes are required? | Suggested that there needs to be a field to identify what piece of information is being changed - also need to know does the whole transaction get re-populated or just the changed fields ? Do we need new fields added to the transaction to accommodate this? |  |  |  |  | Jan 21-06 | GP | Working group
104 | SV | O | Need to confirm the window for sending Add/Updates to an existing pending (before flow) STR. Enbridge will confirm 3 days- need to confirm with Union UK and KU. What about Rescinds- how close to the implementation date can a rescind be actioned? | [5 empty] | Jan 21-07 | GP | Working group
Note on A1: The Global Item Number is a reference # for the Issue.
Note on B1: Workflow refers to the main category process or technical requirement. The values are: SV= Change of Gas Supply from System to Vendor VV= Change of Gas Supply from Vendor to Vendor VS= Change of Gas Supply from Vendor to System CBO = Change of Billing Option CCL = Change of customer location (service address) Tech = Represents issues that refer to technical issues ( ie schema,technical design, data exchange, connectivity etc) Trans= Refers to issues regarding how data is exchanged physically. Other = Used for issues that are of a general nature or can not be fit into the categories above.
Note on C1: Refers to the Status of the issue: O= OPEN -In Progress C = CLOSED- Issue is completed-consensus reached. R = ReferSC- Issue referred to Steering Committee for guidance/decision. Group can not reach Consensus.