## Sheet1
November 28, 2003 Page 1 of 7
ACTION ITEM COMMUNICATION UPDATE
From Union Gas/Enbridge Customer Checkpoint Sessions
As of November 28, 2003
Sorted by: Session, then Item #
Note: Acronym Glossary is Included Below Chart
Session Item # Action Item Union/Enbridge Response
2003-10-08
Business
Checkpoint
1 Can Consumers notifying RTS
via phone? There were
concerns raised by that it
should be done in writing only.
GDAR does not specifically require that the RTS be submitted in writing other than
the rescind of the STR. Union plans to accept RTS requests by phone. Union
notes:
* all requests are documented by CRRs into our source system
* as with other consumer requests, due diligence will be done to ensure the identity
of the requester (e.g. validation terms)
* scripting for RTS will include ensuring consumer acknowledges potential impacts
and encourage them to contact their vendor first
There is an exemption request from EGD on the need for the rescind to be in
writing is currently being evaluated by OEB.
The outcome of this request may dictate the approach.
2003-10-08
Business
Checkpoint
2 How to change effective date
for a processed STR
"Update" action is only available for STRs with a state = "Suspended-AI", per
GDAR. To change the effective date of a processed STR, vendor must submit one
or more other STRs. Example: Add Consumer Nov 1 is processed. To change
effective date to Dec 1, submit a delete consumer request followed by another add
consumer request for Dec 1. To change effective date to Oct 1, submit another
Add Consumer transaction effective Oct 1- the first STR will be marked
"Overwritten".
Notifications are triggered in all cases.
2003-10-08
Business
Checkpoint
3 Can UGL reject for things other
than invalid account number.
Distributors will only mark STRs as "Rejected" if the STR fails.
2003-10-08
Business
Checkpoint
4 Format of Message board
notification
The format of CSV file that will be used for message notifications by Enbridge is
attached. A separate CSV file will be provide for each combination of STR status
(e.g. pending, rescinded, stopped, implemented, or overwritten) and consumer
notification type (e.g. move to a different vendor or move to system gas).
2003-10-08
Business
Checkpoint
5 When will Enbridge and UGL
align on format of the message
board notification?
Enbridge will look align the format of its message board notification with Union
following the implementation of EnTRAC Phase 1. Given existing testing timelines,
it is not feasible to change the existing design prior to implementation. This may
be delivered within the scope of Phase 2 (Sept 2003)
2003-10-08
Business
Checkpoint
6 Consider renaming update
action.
"UpdateConsumer" request will be renamed to "TransferConsumer".
November 28, 2003 Page 2 of 7
Session Item # Action Item Union/Enbridge Response
2003-10-08
Business
Checkpoint
7 Why full response files rather
than partial?
Duplicate item. See response in Technical Items.
2003-10-08
Business
Checkpoint
8 Trans -ID at document level vs.
STR ID #
Duplicate item. See response in Technical Items.
2003-10-08
Business
Checkpoint
9 Will EGD customers who move
out of the franchise area…..be
retained on the existing supply
arrangement on the inactive
account?
Enbridge does not have the capability to maintain an inactive account on an
existing supply arrangement. Once the account is finalized it is removed from the
supply arrangement.
2003-10-08
Business
Checkpoint
10 Do we supply effective date for
customers moving to new
delivery area? Mark to confirm
an earlier "yes" response to this
question.
The earliest effective date will be included. The effective date will be calculated as
the next 1st of the month that is at least 12 days from notification (not requested
move date). Vendors have the ability to update this date. If the update is not timely,
the STR could remain Suspended-AI requesting a new effective date.
2003-10-08
Business
Checkpoint
11 Enbridge to confirm service
address change in comparison
to Union
The Enbridge Service Address Change process will not be identical to that
presented by Union. Enbridge will make best efforts to determine the new
account for a customer that moves within the Enbridge franchise area (the best
manner for doing this is still being determined). This account will be attached to
the agreement under the terms the old account had. If there is a significant time
lag in identifying the new account number, Enbridge will look to the vendor for
confirmation of the contract parameters (pool and price point).
Old accounts will not be retained on the existing supply arrangement as an inactive
account.
2003-10-08
Business
Checkpoint
12 Distribute collision matrix Enbridge and Union have worked to prepare a revised collision matrix that is
consistent between the two organizations. Enbridge is currently preparing this for
distribution, with descriptions to assist in interpreting the matrix. This is expected
to be ready for distribution by December 5 / 03.
2003-10-08
Business
Checkpoint
13 Enbridge to follow up with
format for consumption data
report.
A copy of the Pool Consumption Report specifications for EnTRAC are attached.
2003-10-08
Business
Checkpoint
14 Distribute documentation and
schemas for non-GDAR
Unionline enhancements
Non-GDAR Union Gas schemas will be posted on Union's website at
www.uniongas.com during the week of Dec 1.
2003-10-08
Business
Checkpoint
15 Ability to designate charge to
contract ID for consumption
look up.
Union will continue to ask vendors to designate a charge-to contract up front.
Given the proposed design change to waive charge for the first 5,000 account
each month, this should eliminate charges for ad-hoc users and therefore eliminate
the need for a per-request bill-to contract id.
November 28, 2003 Page 3 of 7
Session Item # Action Item Union/Enbridge Response
2003-10-08
Business
Checkpoint
16 Ability to include consumption
with "ADD" response.
Gas Supply STR is meant to facilitate only a change in gas supply. Addition of this
data would be inconsistent that principle and would not be consistent with EGD.
Union recognizes the discomfort with respect to fee for use and will make the
following adjustment to it's design: In any month, the first 5,000 consumption
requests will not attract a charge. Requests over and above that limit, will attract a
charge of $1.00 per successful history retrieval.
2003-10-08
Business
Checkpoint
17 Consider keeping the contract
id and price point id in the
Monthly Account Activity file.
Union will continue to include the contract id and price point id in the MAA file.
2003-10-09
Technical
Session
1 Distribute Soft copy of
presentation
As per D. Charleson email sent 13-Oct
2003-10-09
Technical
Session
2 Availability and timing of
unattended file transfer for
EGD.
EGD does not have an unattended file transfer within the current scope of
EnTRAC. This decision was based on the fact that no vendors are currently using
the Unionline functionality. EGD will consider providing this functionality as an
enhancement following the implementation of Phase 2 (Sept / 04), if there is
demand from the marketplace.
2003-10-09
Technical
Session
3 Is the Tag name required when
there will not be any value/data
to send with a particular field?
Tag names are not required for optional fields. Some field are nullable. Instance
representation eliminates need to provide empty tag field for non-applicable STR
types
2003-10-09
Technical
Session
4 What are the batch/document
size limitations (i.e. Max. # of
STRs per batch) (UGL/EGD)
Union will increase its transaction count size limitation to 9,000 with the desired
effect to find the optimum balance between the resulting advantages from few
batch submissions and ensuring available processing time is shared equally
between the entire vendor community (as a benchmark reference please note a
batch of 3000 records requires approximately 30 minutes of internal processing
time).
2003-10-09
Technical
Session
5 How do you tie request and
response documents together
(audit/tracking) AND each
subsequent submission of each
record.
Each subsequent submission of each record comes from a new request document
and therefore will be tracked separately in terms of request/response pairings but
the STR tracking itself is maintained. The vendors will be able to track their
documents by the VendorReferenceNumber that they can specify in their request
documents, and is repeated over the multiple response documents that relate to
the original request. In addition, document creation date is being expanded to
include a timestamp to ensure uniqueness of response documents.
2003-10-09
Technical
Session
6 Can the Notification be split per
STR type.
For the non-requestor there is only one STR type (i.e. Delete).
2003-10-09
Technical
Session
7 Response strategy – Option 1 –
return only STRs that have
changed (many responses) vs
return whole batch in response
The current Request and Response strategy (i.e. full Response regardless of
change) will be maintained. Drivers that could trigger a change to an incremental
include adoption of Business to Business (B2B) technology.
November 28, 2003 Page 4 of 7
flagging items that change.
Session Item # Action Item Union/Enbridge Response
2003-10-09
Technical
Session
8 Add functional ability to allow
operator to down load entire
batch with latest states
(assuming Option 1 - STR
response)
See Response October 9th Technical Item #7. Distributors will not be changing its
Response strategy at this time.
2003-10-09
Technical
Session
9 Assign “sequence #” to
response file names (potential
solution requirement)
Duplicate item. See response for October 9 Technical Item 7.
2003-10-09
Technical
Session
10 How many error codes do we
expect to be common and how
many unique (EGD/Union).
Common + Utility+Specific
Reason codes will be defined.
The Utilities have yet to define these codes. They are not expected to be defined
until end of November.
2003-10-09
Technical
Session
11 How to introduce/drop reason
codes, post implementation
A protocol will be developed that is comparable to the protocol proposed for
addressing changes to the common schemas. Protocol should be expanded to
include all changes that impact stakeholders.
2003-10-09
Technical
Session
12 How does Vendor detect and
notify Utility if Utility’s document
is invalid - document & STR
level?
The response documents and notifications should never be invalid at the
document level as they will be built as to the published schemas. Any deviation
from this would be considered an application error that should be reported to the
utility. Questions about the validity of specific STR's should be directed to the
business support contacts within the utility for the applications as the first point of
contact.
2003-10-09
Technical
Session
13 Vendor expressed some
concern that current support
model is inadequate
This was cleared up after a discussion at break. The comments were based on an
early Unionline experience which has since been remedied. Union will continue to
employ the same support model with GDAR implementation.
2003-10-09
Technical
Session
14 Provide documentation on the
security measures (Sapient)
Security considerations have been an important aspect from day one of the design
and implementation of the GDAR solutions for both UG and EGD.
The following are the common security mechanisms built into both solutions:
Authentication: A user cannot access Unionline or EnTRAC unless they have a
valid user id and a password
Authorization: Every user with a unique user id has roles and priveleges assigned
to them in both Unionline and EnTRAC. Based on these priveleges, one vendor
cannot view or updat e the data that belows to another vendor.
Encryption: Both Unionline and EnTRAC use the SSL-based secure http (https)
protocol and employs 128-bit encryption. On the server side, both employ 1024-bit
RSA encrypted certificates issued by a third party. The unattended file transfer
capability in place for Unionline also employs digital certificates issued by a third
party (VeriSign)
November 28, 2003 Page 5 of 7
Architectural security : For both solutions, the technical architecture involves a
standard DMZ (De-Militarized Zone) architectural co
Session Item # Action Item Union/Enbridge Response
2003-10-09
Technical
Session
15 Ability to send STRs with
Vendor specific ID that would
be included in all subsequent
responses (recognized nice to
have).
A new tag is being added to the Gas Supply request/response document for
vendor supplied STR ID. The value will be echoed back in the original first
response only. The vendor would then be required to update their internal systems
to record the utility-defined STR ID.
2003-10-09
Technical
Session
16 Documenting Business Rules
that cause change to states or
collisions
This effort is now expected to be addressed within the GDAR Implementation
Working Group facilitated by the OEB.
2003-10-09
Technical
Session
17 Can there be a single date for a
rollout of the UGL and EGD
GDAR Implementations?
The Utility plans are not currently tied to a single date. Both are working towards
supporting a March 1 GDAR implementation. Internal dependencies may not allow
a common date. Further investigation to be done once implementation plans are
more fully developed.
2003-10-09
Technical
Session
18 Is there flexibility around the
implementation date?
Both Union and Enbridge have limited flexibility given the March 1 GDAR
implementation deadline. Significant changes in the implementation date would
need to be acknowledged by the Ontario Energy Board.
2003-10-09
Technical
Session
19 Vendors to communicate to
UGL & Enbridge any
dependencies or constraints
that they have with respect to
implementation dates for GDAR
Reminder included on 30-Oct communication for Vendors to submit responses.
2003-10-09
Technical
Session
20 Direct requested a Pilot to
assess the possibility of a Pilot
Phase before rolling out the
GDAR Solution.
Union has noted Direct's desire to participate in a pilot program.
2003-10-09
Technical
Session
21 UGL and Enbridge to
coordinate on the GDAR
solution details
communication/educational
Both Utilities are willing to work together on these sessions as they are needed.
Vendors are to identify specific questions or areas requiring additional clarification
to allow for planning of such sessions.
November 28, 2003 Page 6 of 7
sessions preferably have EGD
representation at sessions
being coordinated by Chris
Ripley (UGL).
2003-10-09
Technical
Session
22 Vendors to complete their
review of the schemas at an
attribute level and provide
comments back the Utilities.
Reminder included on 30-Oct communication for Vendors to submit responses.
2003-10-09
Technical
Session
23 Protocol for change
management of common
elements of GDAR solution
post-implementation should be
part of the SLA
This effort is now expected to be addressed within the GDAR Implementation
Working Group facilitated by the OEB.
November 28, 2003 Page 7 of 7
ACRONYM GLOSSARY
B2B
CRR
CSV
EGD
GDAR
MAA
OEB
RTS
SLA
SSL
STR
UGL
Business to Business
Customer Relations Representative
Comma Separated Value
Enbridge Gas Distribution
Gas Distribution Access Rule
Monthly Account Activity
Ontario Energy Board
Return to System
Service Level Agreement
Secure Socket Layer
Service Transaction Request
Union Gas Limited

## GDAR GI List
GI# | WorkFlow | Status | Issue Description | Suggested Resolution | Final Resolution | Schema Affected | Schema Changes Required | Issue Submit Date | Date of Last Status Change | Requestor | Company
001 | VS | O | Can Consumers notify RTS (Return to System) via phone? There were concerns raised that it should be done in writing. | GDAR does not specifically require that the RTS be submitted in writing other than the rescind of the STR. Union plans to accept RTS requests by phone. Union notes: * all requests are documented by CRRs into our source system * as with other consumer requests, due diligence will be done to ensure the identity of the requester (e.g. validation terms) * scripting for RTS will include ensuring consumer acknowledges potential impacts and encourage them to contact their vendor first There is an exemption request from EGD on the need for the rescind to be in writing is currently being evaluated by OEB. The outcome of this request may dictate the approach |  |  |  | Dec 07-03 |  | BC-1 | Union/Enbridge Business Checkpoint Oct 8-
002 | ALL | O | How to change effective date for a processed STR | "Update" action is only available for STRs with a state = "Suspended-AI", per GDAR. To change the effective date of a processed STR, vendor must submit one or more other STRs. Example: Add Consumer Nov 1 is processed. To change effective date to Dec 1, submit a delete consumer request followed by another add consumer request for Dec 1. To change effective date to Oct 1, submit another Add Consumer transaction effective Oct 1- the first STR will be marked "Overwritten". Notifications are triggered in all cases. |  |  |  | Dec 07-03 |  | BC-2 | Union/Enbridge BC Oct 8-
003 | SV- VV | O | Can UGL reject for things other than invalid account number | Distributors will only mark STRs as "Rejected" if the STR fails |  |  |  | Dec 07-03 |  | BC-3 | Union/Enbridge BC Oct 8-
004 | OTHER | O | Format of Message board notification | The format of CSV file that will be used for message notifications by Enbridge is attached. A separate CSV file will be provide for each combination of STR status (e.g. pending, rescinded, stopped, implemented, or overwritten) and consumer notification type (e.g. move to a different vendor or move to system gas). |  |  |  | Dec 07-03 |  | BC-4 | Union/Enbridge BC Oct 8-
005 | OTHER | O | When will Enbridge and UGL align on format of the message board notification? | Enbridge will look align the format of its message board notification with Union following the implementation of EnTRAC Phase 1. Given existing testing timelines, it is not feasible to change the existing design prior to implementation. This may be delivered within the scope of Phase 2 (Sept 2003) |  |  |  | Dec 07-03 |  | BC-5 | Union/Enbridge BC Oct 8-
006 | SV VV VS | O | Consider renaming update action. | "UpdateConsumer" request will be renamed to "TransferConsumer". |  |  |  | Dec 07-03 |  | BC-6 | Union/Enbridge BC Oct 8-
007 | TECH | O | Why full response files rather than partial? |  |  |  |  | Dec 07-03 |  | BC-7 | Union/Enbridge BC Oct 8-
008 | TECH | O | Trans -ID at document level vs. STR ID # |  |  |  |  | Dec 07-03 |  | BC-8 | Union/Enbridge BC Oct 8-
009 | CCL | O | Will EGD customers who move out of the franchise area…..be retained on the existing supply arrangement on the inactive account? | Enbridge does not have the capability to maintain an inactive account on an existing supply arrangement. Once the account is finalized it is removed from the supply arrangement |  |  |  | Dec 07-03 |  | BC-9 | Union/Enbridge BC Oct 8-
010 | CCL | O | Do we supply effective date for customers moving to new delivery area? Mark to confirman earlier "yes" response to this question | The earliest effective date will be included. The effective date will be calculated as the next 1st of the month that is at least 12 days from notification (not requested move date). Vendors have the ability to update this date. If the update is not timely, the STR could remain Suspended-AI requesting a new effective date. |  |  |  | Dec 07-03 |  | BC-10 | Union/Enbridge BC Oct 8-
011 | CCL | O | Enbridge to confirm service address change in comparison to Union | The Enbridge Service Address Change process will not be identical to that presented by Union. Enbridge will make best efforts to determine the new account for a customer that moves within the Enbridge franchise area (the best manner for doing this is still being determined). This account will be attached to the agreement under the terms the old account had. If there is a significant time lag in identifying the new account number, Enbridge will look to the vendor for confirmation of the contract parameters (pool and price point). Old accounts will not be retained on the existing supply arrangement as an inactive account |  |  |  | Dec 07-03 |  | BC-11 | Union/Enbridge BC Oct 8-
012 | SV VV VS | O | Distribute collision matrix Enbridge and Union have worked to prepare a revised collision matrix that is consistent between the two organizations | Enbridge is currently preparing this for distribution, with descriptions to assist in interpreting the matrix. This is expected to be ready for distribution by December 5 / 03. |  |  |  | Dec 07-03 |  | BC-12 | Union/Enbridge BC Oct 8-
013 | OTHER | O | Enbridge to follow up with format for consumption data report | A copy of the Pool Consumption Report specifications for EnTRAC are attached |  |  |  | Dec 07-03 |  | BC-13 | Union/Enbridge BC Oct 8-
014 | OTHER | O | Distribute documentation and schemas for non-GDAR Unionline enhancements | Non-GDAR Union Gas schemas will be posted on Union's website at www.uniongas.com during the week of Dec 1. |  |  |  | Dec 07-03 |  | BC-14 | Union/Enbridge BC Oct 8-
015 | OTHER | O | Ability to designate charge to contract ID for consumption look up | Union will continue to ask vendors to designate a charge-to contract up front. Given the proposed design change to waive charge for the first 5,000 account each month, this should eliminate charges for ad-hoc users and therefore eliminate the need for a per-request bill-to contract id |  |  |  | Dec 07-03 |  | BC-15 | Union/Enbridge BC Oct 8-
016 | OTHER | O | Ability to include consumption with "ADD" response | Gas Supply STR is meant to facilitate only a change in gas supply. Addition of this data would be inconsistent that principle and would not be consistent with EGD. Union recognizes the discomfort with respect to fee for use and will make the following adjustment to it's design: In any month, the first 5,000 consumption requests will not attract a charge. Requests over and above that limit, will attract a charge of $1.00 per successful history retrieval. |  |  |  | Dec 07-03 |  | BC-16 | Union/Enbridge BC Oct 8-
017 | OTHER | O | Consider keeping the contract id and price point id in the Monthly Account Activity file | Union will continue to include the contract id and price point id in the MAA file |  |  |  | Dec 07-03 |  | BC-17 | Union/Enbridge BC Oct 8-
018 | DELETE | O | Distribute Soft copy of presentation | As per D. Charleson email sent 13-Oct |  |  |  | Dec 07-03 |  | TS-1 | Union/Enbridge Technical Checkpoint Oct 9-
019 | TRANS | O | Availability and timing of unattended file transfer for EGD | EGD does not have an unattended file transfer within the current scope of EnTRAC. This decision was based on the fact that no vendors are currently using the Unionline functionality. EGD will consider providing this functionality as an enhancement following the implementation of Phase 2 (Sept / 04), if there is demand from the marketplace. |  |  |  | Dec 07-03 |  | TS-2 | Union/Enbridge TC Oct 9-
020 | TECH | O | Is the Tag name required when there will not be any value/data to send with a particular field | Tag names are not required for optional fields. Some field are nullable. Instance representation eliminates need to provide empty tag field for non-applicable STR types |  |  |  | Dec 07-03 |  | TS-3 | Union/Enbridge TC Oct 9-
021 | TECH | O | What are the batch/document size limitations (i.e. Max. # of STRs per batch) (UGL/EGD) | Union will increase its transaction count size limitation to 9,000 with the desired effect to find the optimum balance between the resulting advantages from few batch submissions and ensuring available processing time is shared equally between the entire vendor community (as a benchmark reference please note a batch of 3000 records requires approximately 30 minutes of internal processing time). |  |  |  | Dec 07-03 |  | TS-4 | Union/Enbridge TC Oct 9-
022 | TECH | O | How do you tie request and response documents together (audit/tracking) AND each subsequent submission of each record | Each subsequent submission of each record comes from a new request document and therefore will be tracked separately in terms of request/response pairings but the STR tracking itself is maintained. The vendors will be able to track their documents by the VendorReferenceNumber that they can specify in their request documents, and is repeated over the multiple response documents that relate to the original request. In addition, document creation date is being expanded to include a timestamp to ensure uniqueness of response documents. |  |  |  | Dec 07-03 |  | TS-5 | Union/Enbridge TC Oct 9-
023 | ?? | O | Can the Notification be split per STR type | For the non-requestor there is only one STR type (i.e. Delete). |  |  |  | Dec 07-03 |  | TS-6 | Union/Enbridge TC Oct 9-
024 | TECH | O | Response strategy – Option 1 – return only STRs that have changed (many responses) vs return whole batch in response flagging items that change | The current Request and Response strategy (i.e. full Response regardless of change) will be maintained. Drivers that could trigger a change to an incremental include adoption of Business to Business (B2B) technology |  |  |  | Dec 07-03 |  | TS-7 | Union/Enbridge TC Oct 9-
025 | TECH | O | Add functional ability to allow operator to down load entire batch with latest states (assuming Option 1 – STR response) | See Response October 9th Technical Item #7. Distributors will not be changing its Response strategy at this time. |  |  |  | Dec 07-03 |  | TS-8 | Union/Enbridge TC Oct 9-
026 | TECH | O | Assign “sequence #” to response file names (potential solution requirement) | Duplicate item. See response for October 9 Technical Item 7. |  |  |  | Dec 07-03 |  | TS-9 | Union/Enbridge TC Oct 9-
027 | ALL | O | How many error codes do we expect to be common and how many unique (EGD/Union). Common + Utility+Specific Reason codes will be defined | The Utilities have yet to define these codes. They are not expected to be defined until end of November. |  |  |  | Dec 07-03 |  | TS-10 | Union/Enbridge TC Oct 9-
028 | OTHER | O | How to introduce/drop reason codes, post implementation | A protocol will be developed that is comparable to the protocol proposed for addressing changes to the common schemas. Protocol should be expanded to include all changes that impact stakeholders |  |  |  | Dec 07-03 |  | TS-11 | Union/Enbridge TC Oct 9-
029 | TECH | O | How does Vendor detect and notify Utility if Utility’s document is invalid - document & STR level? | The response documents and notifications should never be invalid at the document level as they will be built as to the published schemas. Any deviation from this would be considered an application error that should be reported to the utility. Questions about the validity of specific STR's should be directed to the business support contacts within the utility for the applications as the first point of contact |  |  |  | Dec 07-03 |  | TS-12 | Union/Enbridge TC Oct 9-
030 | DELETE | O | Vendor expressed some concern that current support model is inadequate | This was cleared up after a discussion at break. The comments were based on an early Unionline experience which has since been remedied. Union will continue to employ the same support model with GDAR implementation. |  |  |  | Dec 07-03 |  | TS-13 | Union/Enbridge TC Oct 9-
031 | TECH | O | Provide documentation on the security measures (Sapient) | Security considerations have been an important aspect from day one of the design and implementation of the GDAR solutions for both UG and EGD. The following are the common security mechanisms built into both solutions: Authentication: A user cannot access Unionline or EnTRAC unless they have a valid user id and a password Authorization: Every user with a unique user id has roles and priveleges assigned to them in both Unionline and EnTRAC. Based on these priveleges, one vendor cannot view or updat e the data that belows to another vendor. Encryption: Both Unionline and EnTRAC use the SSL-based secure http (https) protocol and employs 128-bit encryption. On the server side, both employ 1024-bit RSA encrypted certificates issued by a third party. The unattended file transfer capability in place for Unionline also employs digital certificates issued by a third party (VeriSign) |  |  |  | Dec 07-03 |  | TS-14 | Union/Enbridge TC Oct 9-
032 | TECH | O | Ability to send STRs with Vendor specific ID that would be included in all subsequentresponses (recognized nice to have) | A new tag is being added to the Gas Supply request/response document for vendor supplied STR ID. The value will be echoed back in the original first response only. The vendor would then be required to update their internal systems to record the utility-defined STR ID |  |  |  | Dec 07-03 |  | TS-15 | Union/Enbridge TC Oct 9-
033 | DELETE | O | Documenting Business Rules that cause change to states or collisions | This effort is now expected to be addressed within the GDAR Implementation Working Group facilitated by the OEB |  |  |  | Dec 07-03 |  | TS-16 | Union/Enbridge TC Oct 9-
034 | OTHER | O | Can there be a single date for a rollout of the UGL and EGD GDAR Implementations? | The Utility plans are not currently tied to a single date. Both are working towards supporting a March 1 GDAR implementation. Internal dependencies may not allow a common date. Further investigation to be done once implementation plans are more fully developed |  |  |  | Dec 07-03 |  | TS-17 | Union/Enbridge TC Oct 9-
035 | OTHER | O | Is there flexibility around the implementation date? | Both Union and Enbridge have limited flexibility given the March 1 GDAR implementation deadline. Significant changes in the implementation date would need to be acknowledged by the Ontario Energy Board |  |  |  | Dec 07-03 |  | TS-18 | Union/Enbridge TC Oct 9-
036 | DELETE | O | Vendors to communicate to UGL & Enbridge any dependencies or constraints that they have with respect to implementation dates for GDAR | Reminder included on 30-Oct communication for Vendors to submit responses |  |  |  | Dec 07-03 |  | TS-19 | Union/Enbridge TC Oct 9-
037 | OTHER | O | Direct requested a Pilot to assess the possibility of a Pilot Phase before rolling out theGDAR Solution. | Union has noted Direct's desire to participate in a pilot program |  |  |  | Dec 07-03 |  | TS-20 | Union/Enbridge TC Oct 9-
038 | DELETE | O | UGL and Enbridge to coordinate on the GDAR solution details communication/educational | Both Utilities are willing to work together on these sessions as they are needed. Vendors are to identify specific questions or areas requiring additional clarification to allow for planning of such sessions. |  |  |  | Dec 07-03 |  | TS-21 | Union/Enbridge TC Oct 9-
039 | DELETE | O | Vendors to complete their review of the schemas at an attribute level and provide comments back the Utilities | Reminder included on 30-Oct communication for Vendors to submit responses |  |  |  | Dec 07-03 |  | TS-22 | Union/Enbridge TC Oct 9-
040 | OTHER | O | Protocol for change management of common elements of GDAR solution post-implementation should be part of the SLA | This effort is now expected to be addressed within the GDAR Implementation Working Group facilitated by the OEB. |  |  |  | Dec 07-03 |  | TS-23 | Union/Enbridge TC Oct 9-
041 | SV |  | Will the Enbridge new home lookup (account number lookup) process work as per the Union Gas documentation? Union documentation demonstrates that if account number is found, customer is enrolled and account number is returned in response file. As per Phase 1A for EnTRAC, a two-step process is required to lookup the account number and then enroll |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
042 | CCL |  | How will customer moves work in each utility? How will we be notified? How do we provide notification? What are the rules at each utility for identifying seamless moves? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
043 | SV VV VS |  | In the workflow section of the documentation, it states that an STR can be moved to a rescind state by and Admin the ‘their’ behalf. On whose behalf? The customer? What are the rules surrounding this being done by EGD? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
044 | SV VV VS |  | Why would an STR move from a pending state to rejected? What scenarios would trigger this transition? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
045 | SV |  | How will the quasi add process work? The map is very limited and does not provide the required detail |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
046 | VV |  | Union documentation indicates that XML notification will be issued to the non-originator of an STR. What will the media for this be for Enbridge? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
047 | CCL |  | For customer moves, the documentation states that this information will be issued in XML format but not posted on the message board. How will the information be transferred to us? What are the schema details? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
048 | ALL |  | Is it possible to receive final transition states (other than rejected) for an STR when processing initial response? For example, can a new add request be responded to with ‘overwritten’ right away? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
049 | OTHER |  | Why will Union Gas not be performing the Security Deposit validation? Will this change and if so, when? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
050 | SV VV VS |  | When do the 14 and 30-day rescission windows start? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
051 | SV VV VS |  | How do STRs become overwritten? Can this occur based on STRs from other brokers? Contextual examples are required here |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
052 | SV |  | Are we notified of all state transitions or will we only receive the current state when the file is generated? For example, if a customer state is pending at 12:00 and the processed at 5:00, will we ever see the pending state? What is the trigger for the update? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
053 | SV VV VS |  | How are new account numbers provided in rejected responses? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
054 | VS |  | Inactive accounts were previously automatically removed from supply agreements upon anniversary maintenance. New documentation states that this will no longer happen. Either the customer? or us must remove the account. How is this to be done? Would the delete transaction be used? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
055 | SV |  | Will there be a unique identifier on accounts that are created as add requests by the utility? How will these accounts be distinguished from accounts that were sent incorrectly by us? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
056 | CCL |  | Documentation indicates that service address changes will ‘always be honoured’. What do this mean? Examples are required |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
057 | SV VV VS |  | If there are already 2 pending STRs, all other incoming STRs will be rejected. Can we attempt the STR again at a later date? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
058 | ALL |  | What are the scenarios that can cause an incoming STR to coexist with a processed STR? Only 1 example was provided |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
059 | OTHER |  | What values other than delivery area will be contained in the ‘additional info’ element? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
060 | OTHER |  | What is the transaction that will be used to request consumption? What are the details of the schema? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
061 | TECH |  | What are the schema details for the supply change notification? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
062 | VV |  | How do we determine the difference between a return to system and a switch to another broker? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
063 | TECH |  | The account number is listed as a required field. How can a required field be left blank? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
064 | SV VV VS |  | For account number lookups, the street number for the customer is required. What about rural addresses? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
065 | TECH |  | Tag is required for customer name when the value is blank. Why is this only required for name and not other values? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
066 | TECH |  | City value is limitted to 20 characters. Is this long enough? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
067 | TECH |  | Gas Vendor Account Number value is limitted to 25 characters. Can this be increased to 50? |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
068 | TECH |  | In the Gas Supply Change Response, the schema document indicates that the status value can be blank. Status must always be returned on a response. Also, reason and reason code should be populated with each response - confirm this for accepted responses |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
069 | TECH |  | Additional information value is required when when we submit to an invalid pool based on delivery area |  |  |  |  | Dec 07-03 |  | Beth Brooks | Direct Energy
070 | TECH |  | Confirm that address information is echoed and not supplimented with utility details in all response records
Note on A1: The Global Item Number is a reference # for the Issue.
Note on B1: Workflow refers to the main category process or technical requirement. The values are: SV= Change of Gas Supply from System to Vendor VV= Change of Gas Supply from Vendor to Vendor VS= Change of Gas Supply from Vendor to System CBO = Change of Billing Option CCL = Change of customer location (service address) Tech = Represents issues that refer to technical issues ( ie schema,technical design, data exchange, connectivity etc) Trans= Refers to issues regarding how data is exchanged physically. Other = Used for issues that are of a general nature or can not be fit into the categories above.
Note on C1: Refers to the Status of the issue: O= OPEN -In Progress C = CLOSED- Issue is completed-consensus reached. R = ReferSC- Issue referred to Steering Committee for guidance/decision. Group can not reach Consensus.