## Alectra Utilities
Schedule for Alectra Utilities Corporation - 2024 Rates ICM
OEB File Number: EB-2023-0004
Updated: October 27, 2023
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [5 empty] | 2023-07-21 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2023-07-25 | 100%
| 3 | OEB Issues Completeness Letter |  | 2023-08-04 | 0 |  | 2023-08-04 | 2023-08-04 | 100%
Notice & Procedural Order No. 1 | 4 | OEB Issues Notice of Hearing | 10 | 2023-08-14 | 6 |  | 2023-08-10 | 2023-08-10 | 100% | Revised letter of direction/notice issued on Aug. 16, 2023
| 5 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2023-08-19 | 11 |  | 2023-08-15 | 2023-08-17 | 100%
| 6 | Intervention Request Close | 25 | 2023-08-29 | 24 |  | 2023-08-28 | 2023-08-28 | 100% | The intervention date was extended from August 25 to August 28 due to the revised letter of direction/notice issued on August 16, 2023.
| 7 | OEB Issues Procedural Order No. 1 | 35 | 2023-09-08 | 26 |  | 2023-08-30 | 2023-08-30 | 100%
Discovery Process | 8 | OEB staff and Intervenors File Interrogatories | 50 | 2023-09-23 | 40 |  | 2023-09-13 | 2023-09-13 | 100%
| 9 | Applicant Files Responses to Interrogatories | 70 | 2023-10-13 | 55 |  | 2023-09-28 | 2023-09-28 | 100%
Argument Process | 10 | OEB staff and Intervenor Argument Filed | 90 | 2023-11-02 | 75 |  | 2023-10-18 | 2023-10-18 | 100%
| 11 | Applicant's Reply Argument Filed | 105 | 2023-11-17 | 90 |  | 2023-11-02
Decision | 12 | Decision Issued | 165 | 2024-02-08 | 150 | 2023-01-25 |  |  |  | Holiday timeout period included (December 16, 2023-January 7, 2024)
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I7
Performance Standard Date = [Performance Standard Days Elapsed]+I7+23
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7