## Enbridge Rates 2024
Schedule for Enbridge Gas Inc.'s Natural Gas Rates beginning 2024
OEB File Number: EB-2022-0200
Updated: September 22, 2023
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Application Filed | 1 | Enbridge Gas Files Part 1 of Application | [5 empty] | 2022-10-31 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2022-11-01 | 100%
| 3 | OEB Issues Letter |  |  | 0 |  | 2022-11-14 | 2022-11-14 | 100% | Letter states that OEB is proceeding with notice
Notice, Completeness & Procedural Order No. 1 | 4 | OEB Issues Notice of Hearing | 10 |  | 0 |  | 2022-11-14 | 2022-11-14 | 100%
| 5 | Last day of publication | 30 | 2022-12-14 | 8 |  | 2022-11-22 | 2022-11-22 | 100%
| 6 | Enbridge Gas Files Part 2 of Application |  |  | 16 |  | 2022-11-30 | 2022-11-30 | 100%
| 7 | Interventions Close | 40 | 2023-01-16 | 18 |  | 2022-12-02 | 2022-12-02 | 100%
| 8 | OEB Issues Completeness Letter |  |  | 32 |  | 2022-12-16 | 2022-12-16 | 100%
| 9 | OEB Issues Procedural Order No. 1 | 60 | 2023-02-05 | 32 |  | 2022-12-16 | 2022-12-16 | 100%
| 10 | HOLIDAY BREAK (DECEMBER 17, 2022 TO JANUARY 7, 2023 INCLUSIVE – 22 DAYS) | [7 empty] | Holiday timeout period
Issues List | 11 | Issues Conference Held |  |  | 34 |  | 2023-01-09 | 2023-01-09 | 100%
| 12 | Submissions on Issues that parties unable to reach consensus |  |  | 41 |  | 2023-01-16 | 2023-01-16 | 100%
| 13 | If parties reach an agreement, OEB staff files proposed issues list |  |  | 42 |  | 2023-01-17 | 2023-01-13 | 100% | Parties reached a partial agreement
| 14 | OEB issues Decision on Issues List & Expert Evidence & Procedural Order No. 2 | [5 empty] | 2023-01-27 | 100%
Intervenor/Staff Evidence Intent Letter | 15 | OEB Staff files Letter on intention to submit evidence |  |  | 36 |  | 2023-01-11 | 2023-01-11 | 100%
| 16 | Intervenors file Letters on intention to submit evidence |  |  | 41 |  | 2023-01-16 | 2023-01-16 | 100%
Discovery | 17 | OEB staff and Intervenors file interrogatories | 90 | 2023-03-06 | 66 |  | 2023-02-10 | 2023-02-10 | 100%
| 18 | Enbridge Gas files responses to interrogatories | 120 | 2023-04-05 | 92 |  | 2023-03-08 | 2023-03-08 | 100% | (March Break 13-17)
| 19 | OEB Issues Procedural Order No. 3 | [5 empty] | 2023-03-17 | 100% | Extending technical conference
| 20 | Technical Conference Begins |  |  | 106 |  | 2023-03-22 | 2023-03-22 | 100%
| 21 | Technical Conference Ends (5 days) | 130 | 2023-04-15 | 115 |  | 2023-03-31 | 2023-03-31 | 100%
| 22 | Undertakings to Technical Conference Filed |  |  | 121 |  | 2023-04-06 | 2023-04-06 | 100%
| 23 | OEB issues Procedural Order No. 4 |  |  | 120 |  |  | 2023-04-05 | 100%
Motions | 24 | Parties file submission on motions |  |  | 125 |  | 2023-04-10 | 2023-04-10 | 100%
| 25 | Applicant files reply submission on motions |  |  | 126 |  | 2023-04-11 | 2023-04-11 | 100%
| 26 | Motions Hearing Held (Re Incomplete IRRs & Undertakings) |  |  | 128 |  | 2023-04-13 | 2023-04-13 | 100%
| 27 | OEB issues Procedural Order No. 5 | [5 empty] | 2023-04-13 | 100%
| 28 | 18 DAYS ADDED TO PROCEDURAL TIMELINE FOR PROCESSSING CASE AS A RESULT OF ENBRIDGE EVIDENCE UPDATE AND ASSOCIATED INCREMENTAL PROCEDURAL STEPS | [7 empty] | The decision target for Phase 1 has been extended by 18 days (355 + 18 days = 373 days)
Additional Evidence | 29 | Enbridge files updated evidence |  |  | 136 |  | 2023-04-21 | 2023-04-21 | 100%
| 30 | Technical Conference held |  |  | 143 |  | 2023-04-27 | 2023-04-27 | 100%
| 31 | Undertakings to Technical Conference Filed |  |  | 149 |  | 2023-05-04 | 2023-05-04 | 100%
Intervenor/Staff Evidence Filed (non Energy Transition) | 32 | OEB Staff and Intervenors file Evidence (not related to energy transition) | 140 | 2023-04-25 | 136 |  | 2023-04-21 | 2023-04-21 | 100%
| 33 | Parties file Interrogatories on Intervenor Evidence (not related to energy transition) | 147 | 2023-05-02 | 143 |  | 2023-04-28 | 2023-04-28 | 100%
| 34 | Responses to Interrogatories on Intervenor Evidence filed (not related to energy transition) | 155 | 2023-05-10 | 160 |  | 2023-05-15 | 2023-05-15 | 100%
Intervenor/Staff Evidence Filed (Energy Transition) | 35 | OEB Staff and Intervenors file Evidence (related to energy transition) |  |  | 156 |  | 2023-05-11 | 2023-05-11 | 100%
| 36 | Applicant files letter on intention to file reply evidence (related to energy transition) |  |  | 160 |  | 2023-05-15 | 2023-05-15 | 100%
| 37 | Parties file Interrogatories on Intervenor Evidence (related to energy transition) |  |  | 162 |  | 2023-05-17 | 2023-05-17 | 100%
| 38 | Responses to Interrogatories on Intervenor Evidence filed (related to energy transition) |  |  | 169 |  | 2023-05-24 | 2023-05-24 | 100%
Settlement Process | 39 | Settlement Conference Begins | 180 | 2023-06-04 | 174 |  | 2023-05-29 | 2023-05-29 | 100%
| 40 | Settlement Conference Ends & Settlement Progress Letter Filed | 183 | 2023-06-07 | 183 |  | 2023-06-07 | 2023-06-09 | 100% | OEB approved a two day extension request
| 41 | OEB issues Procedural Order No. 6 | [5 empty] | 2023-06-23 | 100%
| 42 | Settlement Proposal Filed | 198 | 2023-06-22 | 204 |  | 2023-06-28 | 2023-06-28 | 100%
| 40 | OEB Staff files Submission on Settlement Proposal | 205 | 2023-06-29 | 211 |  | 2023-07-05 | 2023-07-05 | 100%
| 41 | OEB issues Decision on Settlement Proposal | [5 empty] | 2023-08-17 | 100%
Oral Hearing | 42 | Oral Hearing on Unsettled Issues begins | 213 | 2023-07-07 | 219 |  | 2023-07-13 | 2023-07-13 | 100%
| 43 | Oral Hearing Ends | 218 | 2023-07-12 | 248 |  | 2023-08-11 | 2023-08-11 | 100% | 18 oral hearing days
| 44 | OEB issues Letter amending deadlines for steps in Argument stage | [5 empty] | 2023-08-11 | 100%
| 45 | Undertakings from Oral Hearing Filed |  |  | 255 |  | 2023-08-18 | 2023-08-18 | 100%
Argument | 46 | Enbridge Gas files Argument-in-chief | 248 | 2023-08-11 | 258 |  | 2023-08-21 | 2023-08-18 | 100%
| 47 | OEB Staff files Submissions | 268 | 2023-08-31 | 280 |  | 2023-09-12 | 2023-09-12 | 100%
| 48 | Intervenors file Submissions |  |  | 287 |  | 2023-09-19 | 2023-09-19 | 100%
| 49 | Enbridge Gas files Reply Argument | 283 | 2023-09-15 | 309 |  | 2023-10-11 | 2023-10-11 | 100%
| 50 | 12 DAYS ADDED TO PROCEDURAL TIMELINE FOR PROCESSSING CASE AS A RESULT OF EXTENSION REQUESTS TO STEPS IN THE ARGUMENT STAGE, AND ASSOCIATED INCREMENTAL PROCEDURAL STEPS | [7 empty] | The decision target for Phase 1 has been extended by 12 days (355 + 18 days + 12 days = 385 days) based on the difference to the deadline for Enbridge Gas to file its reply argument before and after the extension requests to steps in the argument stage of the proceeding.
| 51 | HOLIDAY BREAK (DECEMBER 16, 2023 TO JANUARY 7, 2024 INCLUSIVE – 23 DAYS) | [7 empty] | Holiday timeout period
Decision | 52 | OEB Issues Decision and Order | 385 | 2024-01-18 | 385 | 2024-01-18 |  |  |  | In accordance with the OEB's performance standards for adjusting timelines, the decision processing time was extended by 18 days to reflect Enbridge Gas’s evidence update and the provision of incremental procedural steps associated with that filing. The decision processing time was extended by another 12 days to reflect granting extension requests to procedural steps in the argument stage. The holiday timeout period extended the decision processing time by 23 days.
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Actual Date = Table12473[[#This Row],[Case Schedule Date Approved]]
Actual Date = Table12473[[#This Row],[Case Schedule Date Approved]]-4
Case Schedule Date Approved = H7+Table12473[[#This Row],[Case Schedule Days Elapsed]]
Case Schedule Date Approved = Table12473[[#This Row],[Case Schedule Days Elapsed]]+H7+22
Performance Standard Date = Table12473[[#This Row],[Performance Standard Days Elapsed]]+H7
Performance Standard Date = Table12473[[#This Row],[Performance Standard Days Elapsed]]+H7+23
Case Schedule Date Planned* = Table12473[[#This Row],[Case Schedule Days Elapsed]]+H7+22+23