## Ottawa River Power
Schedule for Ottawa River Power Corporation - 2022 Cost of Service
OEB File Number: EB-2021-0052
Updated: November 24, 2021
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [5 empty] | 2021-09-30 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2021-10-01 | 100%
| 3 | OEB Issues Incomplete Letter |  |  |  |  | 2021-10-14 | 2021-10-14 | 100%
| 4 | OEB Issues Completeness Letter |  | 2021-10-20 | 0 |  | 2021-10-20 | 2021-10-20 | 100%
Notice & Procedural Order No. 1 | 5 | OEB Issues Notice of Hearing | 10 | 2021-10-30 | 0 |  | 2021-10-20 | 2021-10-20 | 100%
| 6 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2021-11-04 | 6 |  | 2021-10-26 | 2021-10-26 | 100%
| 7 | Notice of Hearing Publication Date |  |  | 8 |  | 2021-10-28 | 2021-10-28 | 100%
| 8 | Intervention Request Close | 25 | 2021-11-14 | 19 |  | 2021-11-08 | 2021-11-08 | 100%
| 9 | OEB Issues Procedural Order No. 1 | 35 | 2021-11-24 | 26 |  | 2021-11-15 | 2021-11-15 | 100%
Discovery Process | 10 | OEB staff Files Draft Issues List | 45 | 2021-12-04 | 33 |  | 2021-11-22 | 2021-11-22 | 100%
| 11 | OEB staff and Intervenors File Interrogatories | 50 | 2021-12-09 | 43 |  | 2021-12-02
| 12 | Applicant Files Responses to Interrogatories | 70 | 2021-12-29 | 63 |  | 2021-12-22
Settlement Process | 13 | Settlement Conference Held (Jan. 10-12, 2022) | 90 | 2022-01-18 | 82 |  | 2022-01-10
| 14 | Settlement Progress Letter Filed |  |  | 89 |  | 2022-01-17
| 15 | Settlement Proposal Filed | 115 | 2022-02-12 | 111 |  | 2022-02-08
| 16 | OEB staff Submission on Settlement Proposal Filed | 122 | 2022-02-19 | 119 |  | 2022-02-16
Hearing | 17 | Presentation of Settlement/Oral Hearing | 130 | 2022-02-27 | 128 | 2022-02-25
Argument Process | 18 | Applicant's Argument-in-chief Filed | 140 | 2022-03-09 | 137 | 2022-03-03
| 19 | OEB staff Argument Filed | 150 | 2022-03-19 | 147 | 2022-03-14
| 20 | Intervenor Argument Filed |  |  | 158 | 2022-03-21
| 21 | Applicant's Reply Argument Filed | 170 | 2022-04-08 | 172 | 2022-04-04
Decision | 22 | Decision Issued | 230 | 2022-06-07 | 231 | 2022-06-02
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I8
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I8