## Renfrew Hydro Inc.
Schedule for Renfrew Hydro Inc.'s 2024 Cost of Service Application
OEB File Number: EB-2023-0049
Updated: November 2, 2023
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [5 empty] | 2023-05-24 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2023-05-29 | 100%
| 3 | OEB Issues Completeness Letter |  |  | 0 |  |  | 2023-06-07 | 100%
Notice & Procedural Order No. 1 | 4 | OEB Issues Notice of Hearing | 10 | 2023-06-17 | 7 |  | 2023-06-14 | 2023-06-14 | 100%
| 5 | Notice of Hearing Publication Date | [5 empty] | 2023-06-22 | 100%
| 6 | Applicant Files Affidavit Confirming Service and Publication | 15 |  |  |  |  | 2023-06-20 | 100%
| 7 | Intervention Requests Close | 25 |  |  |  | 2023-07-04 | 2023-07-04 | 100%
| 8 | OEB Issues Procedural Order No. 1 | 35 | 2023-07-12 | 30 |  | 2023-07-07 | 2023-07-07 | 100%
Issues List | 9 | OEB Staff files proposed issues list | 40 | 2023-07-17 | 40 |  | 2023-07-17 | 2023-07-12 | 100%
| 10 | Decision on Issues List | [5 empty] | 2023-07-25 | 100%
Discovery Process | 11 | OEB Staff and Intervenors File Interrogatories | 60 | 2023-08-06 | 58 |  | 2023-08-04 | 2023-08-04 | 100%
| 12 | Applicant Files Responses to Interrogatories | 80 | 2023-08-26 | 78 |  | 2023-08-24 | 2023-08-24 | 100%
Settlement Process | 13 | Settlement Conference Held (Sept 5-7) | 90 | 2023-09-05 | 90 |  | 2023-09-05 | 2023-09-05 | 100%
| 14 | Applicant files settlement progress letter | [5 empty] | 2023-09-06 | 100%
| 15 | Settlement Proposal Filed | 115 | 2023-09-30 | 114 |  | 2023-09-29 | 2023-09-29 | 100%
Argument Process | 16 | Applicant's Argument-in-Chief Filed | 140 | 2023-10-25 | 131 | 2023-10-16
| 17 | OEB Staff and Intervenors Argument Filed | 150 | 2023-11-04 | 141 | 2023-10-26
| 18 | Applicant's Reply Argument Filed | 170 | 2023-11-24 | 161 | 2023-11-15
HOLIDAY BREAK (DECEMBER 17, 2023 TO JANUARY 6, 2024 INCLUSIVE – 23 DAYS)
Decision | 19 | Decision Issued | 230 | 2024-02-15 | 221 | 2024-02-06 |  | 2023-10-31 | 100% | The Decision is the final step in the schedule.
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I7
Performance Standard Date = [Performance Standard Days Elapsed]+I7+23
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7
Case Schedule Date Planned* = [Case Schedule Days Elapsed]+I7
Case Schedule Date Planned* = [Case Schedule Days Elapsed]+I7+23