## Greater Sudbury
Schedule for Greater Sudbury Hydro Inc. - 2025 Cost of Service
OEB File Number: EB-2024-0026
Updated: March 12, 2025
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Planned | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application
| 2 | OEB Issues Acknowledgement Letter
| 4 | OEB Issues Completeness Letter | 0 | 2024-11-13 | 0 |  |  | 2024-11-13 | 2024-11-13 | 100%
Notice & Procedural Order No. 1 | 5 | OEB Issues Notice of Hearing | 10 | 2024-11-23 | 6 |  |  | 2024-11-19 | 2024-11-19 | 100%
| 6 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2024-11-28 | 7 |  |  | 2024-11-26 | 2024-11-26 | 100%
| 7 | Notice of Hearing Publication Date |  |  | 7 |  |  | 2024-11-20 | 2024-11-26 | 100%
| 8 | Intervention Requests Close | 25 | 2024-12-08 | 23 |  |  | 2024-12-06 | 2024-12-06 | 100%
| 9 | OEB Issues Procedural Order No. 1 | 35 | 2024-12-18 | 28 |  |  | 2024-12-11 | 2024-12-12 | 100%
Discovery Process | 10 | OEB Staff Files proposed Issues List | 45 | 2024-12-28 | 34 |  |  | 2024-12-17 | 2024-12-16 | 100%
HOLIDAY BREAK (DECEMBER 21, 2024 TO JANUARY 3, 2025 INCLUSIVE – 16 DAYS)
| 11 | OEB Staff and Intervenors Files Interrogatories | 60 | 2025-01-28 | 42 |  |  | 2025-01-10 | 2025-01-10 | 100%
| 12 | Applicant Files Responses to Interrogatories | 80 | 2025-02-17 | 67 |  |  | 2025-02-04 | 2025-02-04 | 100%
Settlement Process | 13 | Settlement Conference Held (Feb 10-12) | 90 | 2025-02-27 | 73 |  |  | 2025-02-10 | 2025-02-10 | 100%
| 14 | Applicant files Settlement Progress Letter |  |  | 77 |  |  | 2025-02-14 | 2024-02-14 | 100%
| 15 | Settlement Proposal Filed | 115 | 2025-03-24 | 110 |  |  | 2025-03-19
| 16 | OEB Staff Submission on Settlement Proposal Filed | 122 | 2025-03-31 | 119 |  |  | 2025-03-28
Hearing | 17 | Presentation of Settlement/Oral Hearing | 130 | 2025-04-08 | 125 |  | 2025-04-03
Argument Process | 18 | Applicant's Argument-in-chief Filed | 140 | 2025-04-18 | 133 |  | 2025-04-11
| 19 | OEB Staff and Intervenor Argument Filed | 150 | 2025-04-28 | 143 |  | 2025-04-21
| 20 | Applicant's Reply Argument Filed | 170 | 2025-05-18 | 152 |  | 2025-04-30
Decision | 21 | Decision Issued | 230 | 2025-07-17 | 216 |  | 2025-07-03
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+J7
Performance Standard Date = [Performance Standard Days Elapsed]+J7+16
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7+16
Case Schedule Date Planned = [Case Schedule Days Elapsed]+I7+16